## Project Gantt Chart
[8 empty] | 2025-11-10 | [8 empty] | 2026-01-12 | [7 empty] | 2026-03-09
| Project Start Date: | 2025-11-06 | [5 empty] | 2025-11-10 |  |  |  | 2025-12-08 |  |  |  |  | 2026-01-12 |  |  |  | 2026-02-09 |  |  |  | 2026-03-09 |  |  |  |  | 2026-04-13
| Project Name: | Pre-Trained Hyper-Heuristics For Optimisation Tasks |  |  |  |  | Week starting: | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27
# | Milestone | Deliverable | Start | End | Days | Status | % Done
1 | Pre-trained hyper-heuristic | Construct a hyper-heuristic | 2025-11-03 | bar: 2025-11-03 to 2026-01-12
Pre-train hyper-heuristic | bar: 2025-12-01 to 2026-01-26
2 | Hyper-heuristic metric scores | Evaluate standard HH performance | bar: 2025-12-15 to 2026-01-26
Evaluate pre-trained HH performance | bar: 2025-12-15 to 2026-02-02
Graph Results | bar: 2025-12-22 to 2026-02-16
3 | Integrated web-server | Collect scores from HyFlex HHs | bar: 2026-01-05 to 2026-03-09
Build a compatible web-server bridge | bar: 2026-01-19 to 2026-03-23
Add Python and Java port | bar: 2026-02-09 to 2026-03-30
Compare pre-trained HH with HyFlex | bar: 2026-02-16 to 2026-04-06